## Marketing Plan Data
Marketing Action Plan |  |  |  |  | STATUS COLOR LEGEND & TOGGLE
Marketing Plan Lists
|  | Not Started | In Progress | Delayed | Complete | Custom 1 | Custom 2 | Custom 3 | Custom 4
|  | ON | ON | OFF | ON | OFF | OFF | OFF | OFF
TASK | STATUS | OWNER | ASSIGNED TO | ANTICIPATED START DATE | ANTICIPATED END DATE | ACTUAL START DATE | ACTUAL END DATE | ESTIMATED COST | ACTUAL COST
Website Updates | In Progress | John C. | John C. | 2024-07-01 | 2024-08-01 | 2024-06-28 |  | 1500 | 1250
Monthly Activity Calendars | In Progress | Mark M. | John C. | 2024-07-15 | 2024-08-15 | 2024-07-13 |  | 2000 | 1840
Brochure Design | Complete | Mark M. | John C. | 2024-08-01 | 2024-08-20 |  |  | 1450
Brochure Distribution | Delayed | Kamil A. | Andrew L. | 2024-06-01 | 2024-07-01 | 2024-06-01 | 2024-06-28 | 3000 | 3200
Logo Design | Delayed | Kamil A. | Timothy S. | 2024-09-01 | 2024-09-15 |  |  | 500
Social Media Posts | Delayed | Kamil A. | Vivian A. |  |  |  |  | 575 | 125
Media Monitoring | In Progress | Kamil A. | Gabe F. | 2024-09-12 | 2024-09-25 |  |  | 1750
Surveys | In Progress | Mark M. | Kamil A. | 2024-07-01 | 2024-10-01 | 2024-07-01 |  | 925 | 250
SEO | Not Started | Mark M. | John C. | 2024-07-15 | 2024-08-15 | 2024-07-13 |  | 2000 | 1840
Google Analytics | Delayed | Mark M. | John C. | 2024-08-01 | 2024-08-20 |  |  | 1450
Email Distribution | Complete | Kamil A. | Andrew L. | 2024-06-01 | 2024-07-01 | 2024-06-01 | 2024-06-28 | 3000 | 3200
Partnership Building | Not Started | Kamil A. | Timothy S. | 2024-09-01 | 2024-09-15 |  |  | 500
MARKETING PLAN LISTS

## List Data
Marketing Plan Lists
Marketing Plan Data
NAME | TITLE
John C. | [insert]
Mark M. | [insert]
Kamil A. | [insert]
Phil G. | [insert]
Andrew L. | [insert]
Timothy S. | [insert]
Vivian A. | [insert]
Gabe F. | [insert]
MARKETING PLAN DATA